## 322024
Test case plan
2024-03-02
# | Functionality | Scenario | Description | Notes | Tested by | Android 29 Pixel 2 | Android 31 Pixel 4 | Android 31 Galaxy S23
1 | Startup | App loads | After tapping the app icon, the app loads within 3 seconds |  | Kareem | Passed | Passed | Passed
2 | Losing Turn | Rolling a 5 | If a user rolls a 5 they lose their turn without the ability to solve a problem | Not yet implemented | Kareem | Failed | Failed | Failed
3 | Trying for Jackpot | Rolling a 6 | If a user gets the problem correct they get the jackpot and it resests after | Not yet implemented | Kareem | Failed | Failed | Failed
4 | Adding to jackpot | A user answers question incorrectly | If a user gets the question wrong the value of the question gets added to the jackpot | Not yet implemented | Kareem | Failed | Failed | Failed

## 332024
Test case plan
2024-03-03
# | Functionality | Scenario | Description | Notes | Tested by | Android 29 Pixel 2 | Android 31 Pixel 4 | Android 31 Galaxy S23
1 | Startup | App loads | After tapping the app icon, the app loads within 3 seconds |  | Karee | Passed | Passed | Passed
2 | Losing Turn | Rolling a 5 | If a user rolls a 5 they lose their turn without the ability to solve a problem |  | Kareem | Passed | Passed | Passed
3 | Trying For Jackpot | Rolling a 6 | If a user gets the problem correct they get the jackpot and it resets after | Not yet Implemented | Kareem | Failed | Failed | Failed
4 | Adding to Jackpot | A user answers question incorrectly | If a user gets the question wrong the value of the question gets added to the jackpot | Not Yet Implemented | Kareem | Failed | Failed | Failed

## 342024
Test case plan
2024-03-04
# | Functionality | Scenario | Description | Notes | Tested by | Android 29 Pixel 2 | Android 31 Pixel 4 | Android 31 Galaxy S23
1 | Startup | App loads | After tapping the app icon, the app loads within 3 seconds |  | Karee | Passed | Passed | Passed
2 | Losing Turn | Rolling a 5 | If a user rolls a 5 they lose their turn without the ability to solve a problem |  | Kareem | Passed | Passed | Passed
3 | Trying For Jackpot | Rolling a 6 | If a user gets the problem correct they get the jackpot and it resets after |  | Kareem | Passed | Passed | Passed
4 | Adding to Jackpot | A user answers question incorrectly | If a user gets the question wrong the value of the question gets added to the jackpot |  | Kareem | Passed | Passed | Passed